## Full
Task | Material Cost ($) | Labor Cost (Hours) | Labor Cost ($25/hr) | Total Cost | Labor Cost | 25
Preliminary Design Review
Team Design Meetings | 0 | 144 | 3600 | 3600
Report | 0 | 24 | 600 | 600
Project Plan Schedule
Develop | 0 | 6 | 150 | 150
Aerodynamics and Stability PDR
Aircraft Geometry | 0 | 12 | 300 | 300
Aerodynamic Performance | 0 | 5 | 125 | 125
Stability | 0 | 48 | 1200 | 1200
Propulsion PDR
Propeller Properties | 0 | 30 | 750 | 750
Aerodynamic Propeller Properites | 0 | 5 | 125 | 125
Gearbox Properties | 0 | 0 | 0 | 0
Electric Motor Properties | 0 | 3 | 75 | 75
Procedure Description | 0 | 1 | 25 | 25
Mission Requirements Analysis | 0 | 5 | 125 | 125
Structures and Weights PDR
Landing Gear | 0 | 6 | 150 | 150
Preliminary CAD | 0 | 5 | 125 | 125
Design Strategy
Analysis of Impulsive Loads | 0 | 4 | 100 | 100
Location, Configuraton, Special Structure, Load Analysis | 0 | 18 | 450 | 450
Longitudinal & Lateral tip-over analysis | 0 | 0 | 0 | 0
Tail Strike Analysis | 0 | 2 | 50 | 50
Weight Determination
Center of Gravity | 0 | 3 | 75 | 75
Moments/Products of Inertia | 0 | 0.5 | 12.5 | 12.5
Complete Tabular listing of all parts, locations, weights | 0 | 3 | 75 | 75
Geometric Layout
Geometry of Wing Spars | 0 | 1 | 25 | 25
Location of Wing Ribs & Stringers | 0 | 1 | 25 | 25
Wing Coverings, Materials of Wing Components | 0 | 1 | 25 | 25
Analysis of Wing Loads
V-n Diagram | 0 | 24 | 600 | 600
Max bending/torsional loading coefficients | 0 | 22 | 550 | 550
Load distribution @ max wing loading | 0 | 0.5 | 12.5 | 12.5
Max root bending moment | 0 | 0.5 | 12.5 | 12.5
Final Properties of Wing Box | 0 | 5 | 125 | 125
Assumptions/Failure conditions/Vertical Deflections | 0 | 2 | 50 | 50
Fuselage and Tail Structure
Analysis of Wing Fuselage Attachment | 0 | 2 | 50 | 50
Geometric layout of fuselage structure | 0 | 2 | 50 | 50
Geometric Layout of horizontal tail structure | 0 | 2 | 50 | 50
Geometric Layout of vertical tail structure | 0 | 2 | 50 | 50
Parts Acquisition List
Develop List | 0 | 2 | 50 | 50
CAD, Prototyping, Economic, Test Plan
CAD | 0 | 100 | 2500 | 2500
Manufacturing Report | 0 | 18 | 450 | 450
Build Schedule | 0 | 1 | 25 | 25
Economic Plan | 0 | 3 | 75 | 75
Flight Test Plan | 0 | 1 | 25 | 25
Critical Design Review (CDR)
Presentation Compilation | 0 | 6 | 150 | 150
Presentation Delivery | 0 | 3 | 75 | 75
Aerodynamic Analysis | 0 | 4 | 100 | 100
D&C Analysis | 0 | 6 | 150 | 150
Structural Analysis | 0 | 3 | 75 | 75
Propulsion Analysis | 0 | 4 | 100 | 100
Vehicle Performance Prediction | 0 | 6 | 150 | 150
Unique Aspects | 0 | 1 | 25 | 25
Remaining Design Problems/Solutions | 0 | 1 | 25 | 25
Conclusions | 0 | 1 | 25 | 25
Paper Copies of CDR Slides | 0 | 0.5 | 12.5 | 12.5
Aircraft Manufacturing
Main Wing | 15.352 | 2 | 50 | 65.352
Horizontal Stabilizer | 3.838 | 2 | 50 | 53.838
Vertical Stabilizers | 3.838 | 2 | 50 | 53.838
Fuselage | 5.757 | 4 | 100 | 105.757
Electrical Components | 900 | 0 | 0 | 900
Booms | 160 | 2 | 50 | 210
Landing Gear | 30 | 6 | 150 | 180
Aircraft Assembly
Structural Assembly | 0 | 15 | 375 | 375
Wiring | 40 | 10 | 250 | 290
Individual Component Testing | 0 | 10 | 250 | 250
Flight Test
Flight Readiness Review | 0 | 6 | 150 | 150
"Professional Pilot" Review | 0 | 6 | 150 | 150
System Ground Test | 0 | 12 | 300 | 300
Propulsion Check | 0 | 10 | 250 | 250
Mission Mechanism Check | 0 | 6 | 150 | 150
Overall Flight Test | 0 | 20 | 500 | 500
Final Flight (for score) | 0 | 20 | 500 | 500
Final Project Poster Presentation
Develop | 0 | 20 | 500 | 500
Present | 0 | 6 | 150 | 150
Final Design Report
Develop Report | 0 | 40 | 1000 | 1000
TOTALS: | 1158.785 | 749 | 18725 | 19883.785

## Sums
Task | Material Cost ($) | Labor Cost (Hours) | Labor Cost ($25/hr) | Total Cost | Labor Cost | 25 | Non-Concise
Preliminary Design Review | 0 | 168 | 4200 | 4200
Team Design Meetings | 0 | 144 | 3600 | 3600 |  |  | x
Report | 0 | 24 | 600 | 600 |  |  | x
Project Plan Schedule | 0 | 6 | 150 | 150
Develop | 0 | 6 | 150 | 150 |  |  | x
Aerodynamics and Stability PDR | 0 | 65 | 1625 | 1625
Aircraft Geometry | 0 | 12 | 300 | 300 |  |  | x
Aerodynamic Performance | 0 | 5 | 125 | 125 |  |  | x
Stability | 0 | 48 | 1200 | 1200 |  |  | x
Propulsion PDR | 0 | 44 | 1100 | 1100
Propeller Properties | 0 | 30 | 750 | 750 |  |  | x
Aerodynamic Propeller Properites | 0 | 5 | 125 | 125 |  |  | x
Gearbox Properties | 0 | 0 | 0 | 0 |  |  | x
Electric Motor Properties | 0 | 3 | 75 | 75 |  |  | x
Procedure Description | 0 | 1 | 25 | 25 |  |  | x
Mission Requirements Analysis | 0 | 5 | 125 | 125 |  |  | x
Structures and Weights PDR | 0 | 106.5 | 2662.5 | 2662.5
Landing Gear | 0 | 6 | 150 | 150 |  |  | x
Preliminary CAD | 0 | 5 | 125 | 125 |  |  | x
Design Strategy | [6 empty] | x
Analysis of Impulsive Loads | 0 | 4 | 100 | 100 |  |  | x
Location, Configuraton, Special Structure, Load Analysis | 0 | 18 | 450 | 450 |  |  | x
Longitudinal & Lateral tip-over analysis | 0 | 0 | 0 | 0 |  |  | x
Tail Strike Analysis | 0 | 2 | 50 | 50 |  |  | x
Weight Determination | [6 empty] | x
Center of Gravity | 0 | 3 | 75 | 75 |  |  | x
Moments/Products of Inertia | 0 | 0.5 | 12.5 | 12.5 |  |  | x
Complete Tabular listing of all parts, locations, weights | 0 | 3 | 75 | 75 |  |  | x
Geometric Layout | [6 empty] | x
Geometry of Wing Spars | 0 | 1 | 25 | 25 |  |  | x
Location of Wing Ribs & Stringers | 0 | 1 | 25 | 25 |  |  | x
Wing Coverings, Materials of Wing Components | 0 | 1 | 25 | 25 |  |  | x
Analysis of Wing Loads | [6 empty] | x
V-n Diagram | 0 | 24 | 600 | 600 |  |  | x
Max bending/torsional loading coefficients | 0 | 22 | 550 | 550 |  |  | x
Load distribution @ max wing loading | 0 | 0.5 | 12.5 | 12.5 |  |  | x
Max root bending moment | 0 | 0.5 | 12.5 | 12.5 |  |  | x
Final Properties of Wing Box | 0 | 5 | 125 | 125 |  |  | x
Assumptions/Failure conditions/Vertical Deflections | 0 | 2 | 50 | 50 |  |  | x
Fuselage and Tail Structure | [6 empty] | x
Analysis of Wing Fuselage Attachment | 0 | 2 | 50 | 50 |  |  | x
Geometric layout of fuselage structure | 0 | 2 | 50 | 50 |  |  | x
Geometric Layout of horizontal tail structure | 0 | 2 | 50 | 50 |  |  | x
Geometric Layout of vertical tail structure | 0 | 2 | 50 | 50 |  |  | x
Parts Acquisition List | 0 | 2 | 50 | 50
Develop List | 0 | 2 | 50 | 50 |  |  | x
CAD, Prototyping, Economic, Test Plan | 0 | 123 | 3075 | 3075
CAD | 0 | 100 | 2500 | 2500 |  |  | x
Manufacturing Report | 0 | 18 | 450 | 450 |  |  | x
Build Schedule | 0 | 1 | 25 | 25 |  |  | x
Economic Plan | 0 | 3 | 75 | 75 |  |  | x
Flight Test Plan | 0 | 1 | 25 | 25 |  |  | x
Critical Design Review (CDR) | 0 | 35.5 | 887.5 | 887.5
Presentation Compilation | 0 | 6 | 150 | 150 |  |  | x
Presentation Delivery | 0 | 3 | 75 | 75 |  |  | x
Aerodynamic Analysis | 0 | 4 | 100 | 100 |  |  | x
D&C Analysis | 0 | 6 | 150 | 150 |  |  | x
Structural Analysis | 0 | 3 | 75 | 75 |  |  | x
Propulsion Analysis | 0 | 4 | 100 | 100 |  |  | x
Vehicle Performance Prediction | 0 | 6 | 150 | 150 |  |  | x
Unique Aspects | 0 | 1 | 25 | 25 |  |  | x
Remaining Design Problems/Solutions | 0 | 1 | 25 | 25 |  |  | x
Conclusions | 0 | 1 | 25 | 25 |  |  | x
Paper Copies of CDR Slides | 0 | 0.5 | 12.5 | 12.5 |  |  | x
Aircraft Manufacturing | 1118.785 | 18 | 450 | 1568.785
Main Wing | 15.352 | 2 | 50 | 65.352 |  |  | x
Horizontal Stabilizer | 3.838 | 2 | 50 | 53.838 |  |  | x
Vertical Stabilizers | 3.838 | 2 | 50 | 53.838 |  |  | x
Fuselage | 5.757 | 4 | 100 | 105.757 |  |  | x
Electrical Components | 900 | 0 | 0 | 900 |  |  | x
Booms | 160 | 2 | 50 | 210 |  |  | x
Landing Gear | 30 | 6 | 150 | 180 |  |  | x
Aircraft Assembly | 40 | 35 | 875 | 915
Structural Assembly | 0 | 15 | 375 | 375 |  |  | x
Wiring | 40 | 10 | 250 | 290 |  |  | x
Individual Component Testing | 0 | 10 | 250 | 250 |  |  | x
Flight Test | 0 | 80 | 2000 | 2000
Flight Readiness Review | 0 | 6 | 150 | 150 |  |  | x
"Professional Pilot" Review | 0 | 6 | 150 | 150 |  |  | x
System Ground Test | 0 | 12 | 300 | 300 |  |  | x
Propulsion Check | 0 | 10 | 250 | 250 |  |  | x
Mission Mechanism Check | 0 | 6 | 150 | 150 |  |  | x
Overall Flight Test | 0 | 20 | 500 | 500 |  |  | x
Final Flight (for score) | 0 | 20 | 500 | 500 |  |  | x
Final Project Poster Presentation | 0 | 26 | 650 | 650
Develop | 0 | 20 | 500 | 500 |  |  | x
Present | 0 | 6 | 150 | 150 |  |  | x
Final Design Report | 0 | 40 | 1000 | 1000
Develop Report | 0 | 40 | 1000 | 1000 |  |  | x
TOTALS: | 1158.785 | 749 | 18725 | 19883.785