## Sheet1
Task | Material Cost ($) | Labor Cost (Hours) | Labor Cost ($25/hr) | Total Cost | Labor Cost | 25
Preliminary Design Review
Team Design Meetings | 0 | 144 | 3600 | 3600
Report | 0 | 24 | 600 | 600
Project Plan Schedule
Develop | 0 | 6 | 150 | 150
Aerodynamics and Stability PDR
Aircraft Geometry | 0 | 12 | 300 | 300
Aerodynamic Performance | 0 | 5 | 125 | 125
Stability | 0 | 48 | 1200 | 1200
Propulsion PDR
Propeller Properties | 0 | 30 | 750 | 750
Aerodynamic Propeller Properites | 0 | 5 | 125 | 125
Gearbox Properties | 0 | 0 | 0 | 0
Electric Motor Properties | 0 | 3 | 75 | 75
Procedure Description | 0 | 1 | 25 | 25
Mission Requirements Analysis | 0 | 5 | 125 | 125
Structures and Weights PDR
Landing Gear | 0 | 6 | 150 | 150
Preliminary CAD | 0 | 5 | 125 | 125
Design Strategy
Analysis of Impulsive Loads | 0 | 4 | 100 | 100
Location, Configuraton, Special Structure, Load Analysis | 0 | 18 | 450 | 450
Longitudinal & Lateral tip-over analysis | 0 | 0 | 0 | 0
Tail Strike Analysis | 0 | 2 | 50 | 50
Weight Determination
Center of Gravity | 0 | 3 | 75 | 75
Moments/Products of Inertia | 0 | 0.5 | 12.5 | 12.5
Complete Tabular listing of all parts, locations, weights | 0 | 3 | 75 | 75
Geometric Layout
Geometry of Wing Spars | 0 | 1 | 25 | 25
Location of Wing Ribs & Stringers | 0 | 1 | 25 | 25
Wing Coverings, Materials of Wing Components | 0 | 1 | 25 | 25
Analysis of Wing Loads
V-n Diagram | 0 | 24 | 600 | 600
Max bending/torsional loading coefficients | 0 | 22 | 550 | 550
Load distribution @ max wing loading | 0 | 0.5 | 12.5 | 12.5
Max root bending moment | 0 | 0.5 | 12.5 | 12.5
Final Properties of Wing Box | 0 | 5 | 125 | 125
Assumptions/Failure conditions/Vertical Deflections | 0 | 2 | 50 | 50
Fuselage and Tail Structure
Analysis of Wing Fuselage Attachment | 0 | 2 | 50 | 50
Geometric layout of fuselage structure | 0 | 2 | 50 | 50
Geometric Layout of horizontal tail structure | 0 | 2 | 50 | 50
Geometric Layout of vertical tail structure | 0 | 2 | 50 | 50
Parts Acquisition List
Develop List | 0 | 2 | 50 | 50
CAD, Prototyping, Economic, Test Plan
CAD | 0 | 100 | 2500 | 2500
Manufacturing Report | 0 | 18 | 450 | 450
Build Schedule | 0 | 1 | 25 | 25
Economic Plan | 0 | 3 | 75 | 75
Flight Test Plan | 0 | 1 | 25 | 25
Critical Design Review (CDR)
Presentation Compilation | 0 | 6 | 150 | 150
Presentation Delivery | 0 | 3 | 75 | 75
Aerodynamic Analysis | 0 | 4 | 100 | 100
D&C Analysis | 0 | 6 | 150 | 150
Structural Analysis | 0 | 3 | 75 | 75
Propulsion Analysis | 0 | 4 | 100 | 100
Vehicle Performance Prediction | 0 | 6 | 150 | 150
Unique Aspects | 0 | 1 | 25 | 25
Remaining Design Problems/Solutions | 0 | 1 | 25 | 25
Conclusions | 0 | 1 | 25 | 25
Paper Copies of CDR Slides | 0 | 0.5 | 12.5 | 12.5
Aircraft Manufacturing
Main Wing | 15.352 | 2 | 50 | 65.352
Horizontal Stabilizer | 3.838 | 2 | 50 | 53.838
Vertical Stabilizers | 3.838 | 2 | 50 | 53.838
Fuselage | 5.757 | 4 | 100 | 105.757
Electrical Components | 900 | 0 | 0 | 900
Booms | 160 | 2 | 50 | 210
Landing Gear | 30 | 6 | 150 | 180
Aircraft Assembly
Structural Assembly | 0 | 15 | 375 | 375
Wiring | 40 | 10 | 250 | 290
Individual Component Testing | 0 | 10 | 250 | 250
Flight Test
Flight Readiness Review | 0 | 6 | 150 | 150
"Professional Pilot" Review | 0 | 6 | 150 | 150
System Ground Test | 0 | 12 | 300 | 300
Propulsion Check | 0 | 10 | 250 | 250
Mission Mechanism Check | 0 | 6 | 150 | 150
Overall Flight Test | 0 | 20 | 500 | 500
Final Flight (for score) | 0 | 20 | 500 | 500
Final Project Poster Presentation
Develop | 0 | 20 | 500 | 500
Present | 0 | 6 | 150 | 150
Final Design Report
Develop Report | 0 | 40 | 1000 | 1000
TOTALS: | 1158.785 | 749 | 18725 | 19883.785